## Gantt Chart
AirlineCRM Gantt Chart
Project Start | 2026-09-30 | Project Finish | 2026-11-28 | Calendar Duration | 60
[6 empty] | September 2026 | October 2026 | [30 empty] | November 2026
Task ID | Task Name | Predecessor(s) | Duration (Days) | Start Date | Finish Date | time axis 2026-09-30 to 2026-11-28
T1 | Requirements finalization and architecture planning | — | 5 | 2026-09-30 | 2026-10-04 | bar: 2026-09-30 to 2026-10-04
T2 | Database design and build | T1 | 7 | 2026-10-05 | 2026-10-11 | bar: 2026-10-05 to 2026-10-11
T3 | User interface design and prototype review | T1 | 6 | 2026-10-05 | 2026-10-10 | bar: 2026-10-05 to 2026-10-10
T4 | Authentication and role-based access control | T2, T3 | 8 | 2026-10-12 | 2026-10-19 | bar: 2026-10-12 to 2026-10-19
T5 | Customer profile, search and booking history | T4 | 10 | 2026-10-20 | 2026-10-29 | bar: 2026-10-20 to 2026-10-29
T6 | Service request and notification module | T5 | 9 | 2026-10-30 | 2026-11-07 | bar: 2026-10-30 to 2026-11-07
T7 | Loyalty and feedback module | T5 | 7 | 2026-10-30 | 2026-11-05 | bar: 2026-10-30 to 2026-11-05
T8 | B2B and partner account module | T5 | 6 | 2026-10-30 | 2026-11-04 | bar: 2026-10-30 to 2026-11-04
T9 | Segmentation and campaign module | T6, T7 | 6 | 2026-11-08 | 2026-11-13 | bar: 2026-11-08 to 2026-11-13
T10 | Reporting and dashboard module | T8, T9 | 6 | 2026-11-14 | 2026-11-19 | bar: 2026-11-14 to 2026-11-19
T11 | Integration and system testing | T10 | 9 | 2026-11-20 | 2026-11-28 | bar: 2026-11-20 to 2026-11-28